## Dashboard
Week Of:
3/16/20 - 3/20/2015
Active Projects
| Project Name | Customer | Priority | Start Date | Customer Trial Start Date | Project End Date | Previous Weeks Project End date | Delta in End Date | Status | Dev Owoner/ Int Owner | Project Health | Notes /Major Change
| STB Probe Phase 1 | ResTel | High | 2015-01-28 | 2015-04-22 | 2015-05-05 | 2015-05-22 | -17 | dev in progress | Cazey Zebrowski/ Chris Nett |  | Wrapping up the last features in the alpha phase, on track to be completed by Tuesday.
| PF Installer | Hawaiian Telecom /Hotwire/Tbaytel | High | 2015-02-09 | 2015-03-05 | 2015-03-27 | 2015-04-09 | -13 | trial in progress, installed in Tybaltel | Josh Lewish / Shon N |  | There is a problem with the DVR feature, dev work is on hold until work is done on the CSR Tool
| Client Diagnostic | Hawaiian Telecom | High | 2015-01-12 | 2015-02-05 | 2015-04-09 | 2015-03-24 | 16 | In Trial in HT | Pidex Inc./Chris Nett |  | Customer Trial have been extended to the end of March
| CSR Tool Phase 1 | Hawaiian Telecom /Hotwire | High | 2015-02-16 | 2015-03-27 | 2015-04-13 | 2015-05-19 | -36 | In Dev of Phase 1 | Johnny Lo/ Chris Nett |  | Moved Johnny as the dev resource to complete phase 1, final is at risk of slipping
| CSR Tool Phase 2 | Hotwire | High | 2015-04-02 | 2015-05-05 | 2015-06-05 | 2015-05-19 | 17 | Waiting on resources to be freeded up | Johnny/Chris Nett |  | Final date is at risk due to resouces delay
| SQL Reporting | Century Link | High | 2014-12-24 | - | 2015-03-23 | 2015-03-20 | 3 | Final report being generated | Johnny Lo |  | Final report will be delivered by Jason on Monday
| Capacity Monitor | Hotwire | High | 2015-01-05 | 2015-04-21 | 2015-05-21 | 2015-06-01 | -11 | In Dev | Pidex Inc./ Joe D. |  | Reduced the scope to remove Dashboard and keeping with the timeline.
| A-Server Script | Telus | High | 2015-02-09 | 2015-03-06 | 2015-03-20 | 2015-03-13 | 7 | Testing in Telus Env in progress | Yean Chan |  | First round of testing complete, blocking issues found. Waiting on Telus to get back from vacation to set a new time to test to run the test again. Date pusehd to 3/20
| SCOM MP Phase 1 | Telus /Hotwire | Medium | 2015-02-02 | - | 2015-04-01 | 2015-03-11 | 21 | dev in progress | Russl Slaton / Yean Chan |  | Scope was updated, causing the dev complete date to be pushed out to 3/20/2015
| SCOM MP Phase 2 | Telus/Hotwire | Medium | 2015-04-02 | - | 2015-05-07 | - | - | Planning Phase | Pidex/ Yean Chan
| PIN Reset | Maxcom | Medium | 2015-02-02 | - | 2015-03-24 | 2015-03-20 | 4 | In Dev. | Vithoba Knot/Chris Nett |  | The last build introduced an error in how the accounts where being logged
| Self Subcribe | Maxcom | Medium | 2015-03-06 | 2015-05-16 | 2015-06-02 | 2015-05-22 | 11 | POC in progress | Vithoba Knot/Yean Chan |  | POC in progress
| Client Monitor - Hot Fix | Century Link | Low | 2015-02-26 | - | 2015-03-18 | 2015-03-02 | 16 | Dev complete | David Collacott |  | We are still having a time out problem and a problem with deleting large files
| PF Self Help | Tbaytel | Low | 2015-01-05 | 2015-03-23 | 2015-04-09 | 2015-04-07 | 2 | dev in progress | Vithoba Knot/Chris Nett |  | Still a number of bugs filed under the beta phase in the project. Beta to be complete next week
| Client Sniffer 2.0.1 | Hawiann Telecom | Low | 2015-01-12 | 2015-02-23 | 2015-03-06 | 2015-03-09 | -3 | trial in progress | David Collacott |  | Installed and waiting for feedback
| Client Sniffer 2.0.1 | Bell Cananda | Low | 2015-01-12 | 2015-02-23 | 2015-03-06 | 2015-03-09 | -3 | trial in progress | David Collacott |  | Waiting on the go ahead to install in HT
| Data Analysis Platform Phase 1 | - | Low | 2015-03-09 | - | 2015-04-03 | - | - | Dev | Johnny Lo
Active Trials
| Project Name | Customer |  | Start Date |  | End Date
| Client Diagnostic | Hawaiian Telecom |  | 2015-02-05 |  | 2015-03-31
| Client Sniffer 2.0.1 | Hawaiian Telecom |  | 2015-02-23 |  | 2015-03-02
| Client Sniffer 2.0.1 | Bell Cananda |  | 2015-02-23 |  | 2015-03-02

## Customer Installs
Customer | Product Name | Start Date | End Date | Duration | Version | Owner | Status | Prerequisites/notes
Century Link
| SQL Reporting |  |  |  |  | Century Link
| Beta Install | 2015-02-27 | 2015-03-05 |  | 1 |  | complete
| Finall Install | 2015-03-26 | 2015-03-26 |  | 1 |  | complete
Hawian Telecom
| Client Diagnostic |  |  |  | 1
| Final Install | 2015-03-23 | 2015-03-23 |  |  | Chris Nett
| Client Sniffer |  |  |  | 2.0.1
| Final Install | 2015-03-10 | 2015-03-10 |  |  | Joe Di Vincenzo
| PF Installer |  |  |  | 1
| Beta Install | 2015-02-23 | 2015-02-26 |  |  | Josh Lewis | completed
| Final Install | 2015-04-09 | 2015-04-09 |  |  | Shon Nadeau
CSR Tool Phase 1
| EC Kickoff | 2015-03-11 | 2015-03-12
| Beta Install | 2015-03-16 | 2015-03-16 |  |  | Josh Lewis
| CSR Tool Phase 2 |  |  |  | 1.5
| Beta Install | 2015-04-17 | 2015-03-16 |  |  | Shon Nadeau
| Final Install | 2015-05-19 | 2015-05-19 |  |  | Shon Nadeau
Telus |  | 1
| Mediaroom power1 schell |  |  |  | 1
| Beta Install |  |  |  |  | Yean Chan
| Finall Install |  |  |  |  | Yean Chan
| Classificaiton Mangement Pack |  |  |  | 1
| Beta Install |  |  |  |  | Yean Chan
| Finall Install |  |  |  |  | Yean Chan
| SCOM Alert Handling Web Application |  |  |  | 1
| Beta Install |  |  |  |  | Jeff W
| Finall Install |  |  |  |  | Jeff W
| A-Sever |  |  |  | 1
| Final Install | 2015-03-06 | 2015-03-13 |  |  | Yean Chan
Tbaytel
| PF Self Help |  |  |  | 1
EC Kickoff
| Beta Install | 2015-03-13 | 2015-03-16 |  |  | Chris Nett
| Finall Install | 2015-03-16 | 2015-03-16 |  |  | Chris Nett
| PF Installer | [6 empty] | Dependson completing HT install
| EC Kickoff | 2015-03-05 | 2015-03-12 |  |  | Shon Nadeau
| Beta Install | 2015-03-13 | 2015-03-13 |  |  | Shon Nadeau |  | Installed but there are bugs
| Finall Install | 2015-04-10 | 2015-04-10 |  |  | Shon Nadeau
Hotwire
CSR Tool Phase 2
| EC Kickoff | 2015-04-02 | 2015-04-03 |  |  | Chris Nett
| Beta Install | 2015-04-16 | 2015-04-19 |  |  | Chris Nett
| Finall Install | 2015-05-19 | 2015-05-21 |  |  | Chris Nett
| PF Installer | [6 empty] | Dependson completing Tbaytel install
| EC Kickoff | 2015-03-06 | 2015-03-13 |  |  | Shon Nadeau
| Beta Install | 2015-03-16 | 2015-03-16 |  |  | Shon Nadeau
| Finall Install | 2015-04-11 | 2015-04-11 |  |  | Shon Nadeau
Bell Cananda
Client Sniffer
| Finall Install | 2015-03-10 | 2015-03-10 |  |  | David Collacott
Lumos
Restel
| STB Probe Phase 1 |  |  |  | 1
| EC Kickoff | 2015-05-22 | 2015-05-23 |  |  | Chris Nett
| Beta Install | 2015-06-05 | 2015-06-05 |  |  | Chris Nett
| Finall Install | 2015-06-18 | 2015-06-18 |  |  | Chris Nett
STB Probe Phase 2
| EC Kickoff | 2015-07-16 | 2015-07-17 |  |  | Yean Chan
| Beta Install | 2015-07-30 | 2015-07-30 |  |  | Yean Chan
| Finall Install | 2015-08-11 | 2015-08-11 |  |  | Yean Chan
ATT
| R-UPD |  |  |  | 1
| EC Kickoff | 2015-10-01 | 2015-10-02 |  |  | Yean Chan
| Beta Install | 2015-10-15 | 2015-10-15 |  |  | Yean Chan
| Finall Install | 2015-11-11 | 2015-11-11 |  |  | Yean Chan
Park Region
| Client Montior |  |  |  | 1
Tyler Williams
| Beta Install |  |  |  |  | Tyler Williams
| Finall Install |  |  |  |  | Tyler Williams
Formulas:
Start Date = [Start Date, row below]-5
End Date = [Start Date]+1

## Projects Timelines
Resource Name- Project Name | Start Date | End Date | Duration
ATT POC for Decryptor | 2015-02-02 | 2015-02-27 | 25
ATT: Decryptor | 2015-03-01 | 2015-06-30 | 121
Client Diagnostic | 2015-01-12 | 2015-04-09 | 87
CSR Tool Phase 1 | 2015-02-16 | 2015-04-13 | 56
SQL Reporting | 2014-12-24 | 2015-03-23 | 89
Century Link Poster Art | 2015-02-02 | 2015-02-13 | 11
Capacity Monitor | 2015-01-05 | 2015-05-21 | 136
STB Probe Phase 1 | 2015-01-28 | 2015-05-05 | 97
STB Probe Phase 2 | 2015-06-01 | 2015-07-15 | 44
A-Server Script | 2015-02-09 | 2015-03-20 | 39
PIN Reset | 2015-02-02 | 2015-03-24 | 50
Self Subcribe | 2015-03-06 | 2015-05-22 | 77
VOD Management Tool | 2015-05-13 | 2015-06-16 | 34
SCOM MP Phase 1 | 2015-02-02 | 2015-04-01 | 58
SCOM MP Phase 2 | 2015-04-02 | 2015-05-07 | 35
ATT: R-UDP Web App | 2015-05-15 | 2015-11-11 | 180
Client Sniffer 2.0.1 | 2015-01-12 | 2015-03-06 | 53
PF Self Help | 2015-01-05 | 2015-04-09 | 94
Health check Tool | 2015-03-17 | 2015-03-30 | 13
PF Installer | 2015-02-09 | 2015-03-27 | 46
Client Sniffer 2.1 | 2015-05-17 | 2015-08-03 | 78
TV2 Shared Library | 2015-04-01 | 2015-05-31 | 60
TV2 Automation Integration | 2015-07-01 | 2015-08-30 | 60
Client Monitor 3.0 | 2015-08-04 | 2016-01-03 | 152
Data Analysis Platform Phase 1 | 2015-03-09 | 2015-04-03 | 25
CSR Tool Phase 2 | 2015-04-02 | 2015-06-05 | 64
Client Monitor 2.1 | 2015-03-23 | 2015-04-03 | 11
Health Check Tool 2.0 | 2015-03-23 | 2015-06-01 | 70
Deployment Automation | 2015-04-06 | 2015-04-21 | 15
HT SQL Reporting | 2015-04-22 | 2015-05-19 | 27
Client Diagnostic MR | 2015-08-18 | 2015-09-09 | 22
CSR Tool MR | 2015-09-28 | 2015-10-19 | 21
Capacity Monitor MR | 2015-09-17 | 2015-10-08 | 21
PF Self Help MR | 2015-08-07 | 2015-08-28 | 21
PIN Reset MR | 2015-07-15 | 2015-08-05 | 21
STB Probe MR | 2015-11-20 | 2015-12-16 | 26
VOD Management Tool MR | 2015-10-23 | 2015-11-12 | 20
Self Subcribe MR | 2015-09-21 | 2015-10-12 | 21
PF Installer MR | 2015-08-11 | 2015-09-01 | 21
Client Sniffer MR
API Client Monitor | 2015-03-24 | 2015-04-10 | 17
Formulas:
End Date = [Start Date]+78

## Dev
Resource Name-Project Name | Start Date | End Date | Duration | Percent Dedicated
Casey Zebrowski
STB Probe Phase 1 | 2015-01-28 | 2015-05-05 | 97
VOD Management Tool | 2015-05-13 | 2015-06-16 | 30
David Collacott
Telus Load Testing | 2015-01-05 | 2015-04-03 | 88
Client Sniffer 2.0.1 | 2015-01-12 | 2015-03-06 | 53
CSR Tool Phase 1 | 2015-02-02 | 2015-02-06 | 4
Client Monitor 2.1 | 2015-03-23 | 2015-04-03 | 11
Deployment Automation | 2015-04-06 | 2015-04-21 | 15
HT SQL Reporting | 2015-04-22 | 2015-05-19 | 27
Client Sniffer 2.1 | 2015-05-17 | 2015-08-03 | 78
Client Monitor 3.0 | 2015-08-04 | 2016-01-03 | 152
Johnny Lo
SQL Reporting | 2014-12-24 | 2015-03-23 | 89
Century Link Poster Art | 2015-02-02 | 2015-02-13 | 11
CSR Tool Phase 1 | 2015-02-16 | 2015-04-13 | 56
Data Analysis Platform Phase 1 | 2015-03-09 | 2015-04-03 | 25
ATT: R-UDP Web App | 2015-05-15 | 2015-11-11 | 180
API Client Monitor | 2015-03-24 | 2015-04-10 | 17
Josh Lewis
CSR Tool Phase 2 | 2015-04-02 | 2015-06-05 | 64
TV2 Shared Library | 2015-04-01 | 2015-05-31 | 60
ATT: R-UDP Web App | 2015-05-15 | 2015-11-11 | 180
Vithoba Khot
PF Self Help | 2015-01-05 | 2015-04-09 | 94
PIN Reset | 2015-02-02 | 2015-03-24 | 50
Self Subcribe | 2015-03-06 | 2015-05-22 | 77
PF Installer | 2015-05-01 | 2015-05-15 | 14
Client Diagnostic MR | 2015-08-18 | 2015-09-09 | 22
CSR Tool MR | 2015-09-28 | 2015-10-19 | 21
Capacity Monitor MR | 2015-09-17 | 2015-10-08 | 21
PF Self Help MR | 2015-08-07 | 2015-08-28 | 21
PIN Reset MR | 2015-07-15 | 2015-08-05 | 21
STB Probe MR | 2015-11-20 | 2015-12-16 | 26
VOD Management Tool MR | 2015-10-23 | 2015-11-12 | 20
Self Subcribe MR | 2015-09-21 | 2015-10-12 | 21
PF Installer MR | 2015-08-11 | 2015-09-01 | 21
Client Sniffer MR

## Ops
Resource Name- Project Name | Start Date | End Date | Duration | Percent Dedicated
Yean Chan
A-Server Script | 2015-02-09 | 2015-03-20 | 39
SCOM MP Phase 1 | 2015-02-02 | 2015-04-01 | 58
SCOM MP Phase 2 | 2015-04-02 | 2015-05-07 | 35
PF Installer | 2015-02-09 | 2015-03-27 | 46
Health check Tool | 2015-03-17 | 2015-03-30 | 13
VOD Management Tool | 2015-05-13 | 2015-06-16 | 34
STB Probe Phase 2 | 2015-06-01 | 2015-07-15 | 44
TV2 Shared Library | 2015-04-01 | 2015-05-31 | 60
TV2 Automation Integration | 2015-07-01 | 2015-08-30 | 60
Data Analysis Platform Phase 1 | 2015-03-09 | 2015-04-03 | 25
Chris Net
PF Self Help | 2015-01-05 | 2015-04-09 | 94
Client Diagnostic | 2015-01-12 | 2015-04-09 | 87
CSR Tool Phase 1 | 2015-02-16 | 2015-04-13 | 56
CSR Tool Phase 2 | 2015-04-02 | 2015-06-05 | 64
Self Subcribe | 2015-03-06 | 2015-05-22 | 77
STB Probe Phase 1 | 2015-01-28 | 2015-05-05 | 97
ATT: R-UDP Web App | 2015-05-15 | 2015-11-11 | 180
Joe Di Vincenzo
Client Sniffer 2.0.1 | 2015-01-12 | 2015-03-06 | 53
Capacity Monitor | 2015-01-05 | 2015-05-21 | 136
Client Sniffer 2.1 | 2015-05-17 | 2015-08-03 | 78
Shon Nadeau
PF Installer | 2015-02-09 | 2015-03-27 | 46

## Customer Trials
Customer | Product Name | Start Date | End Date | Duration | Prerequisites | Stuatus
Century Link
| SQL Queries |  |  |  |  | no demo required
Hawian Telecom
| Client Diagnsistics | 2015-02-05 | 2015-03-31 | 54
| Client Sniffer 2.0.1-Client | 2015-02-23 | 2015-03-02 | 7
| PF Installer | 2015-03-05 | 2015-03-31 | 26
| CSR Tool -Phase 1 | 2015-03-27 | 2015-04-10 | 14
SCOM MP
Telus
SCOM MP
Mediaroom power1 schell
Critial Mops
Classificaiton Mangement Pack
SCOM Alert Handling Web Application
| A-Sever | 2015-03-06 | 2015-03-18 | 12
Health Check
Tbaytel
| PF Self Help | 2015-03-23 | 2015-04-03 | 11
| CSR Tool Phase 2 - Trial | 2015-05-05 | 2015-05-18 | 13
Hotwire
| CSR Tool Phase 2 - Trial | 2015-05-05 | 2015-05-18 | 13
| PF Installer |  |  |  | Installed and tested in HT
| Capacity Monitor | 2015-04-21 | 2015-05-04
Bell Cananda | Client Sniffer | 2015-02-23 | 2015-03-02 | 7
Client Monitor
Lumos | R-DVR |  |  |  |  | installed
| Caller ID |  |  |  |  | installed
Maxcom
| PIN Rest | 2015-03-04 | 2015-03-09
VOD Mangement
STB Reset
| Self Subcribe | 2015-05-16 | 2015-05-22
`
ATT
| R-UPD | 2015-10-22 | 2015-10-28
Restel
| STB Probe Phase 1 | 2015-04-22 | 2015-04-28 | 6