## SalesForce Project Plan
Sales Force Phase 1 | 2015-01-30
Task | Description | Dependencies | Owner (s) | Start Date | Completion Date | Duration | Status | Notes
1. Non-Profit Starter Pack | [5 empty] | 0
a. Install Non-Profit Starter Pack | Install NPSP on IAM Salesforce instance | none | Dipesh | 2015-01-30 | 2015-02-01 | 2 | Complete
b. Configure Non-Profit Starter Pack | Determine which objects and fields will IAM need | 1a | Dipesh, Ben | 2015-02-01 | 2015-02-05 | 4 | Complete
c. Basic Data Structure | Determine the basic data structure and flow | 1a, 1b | Dipesh, Ben | 2015-02-05 | 2015-02-10 | 5 | Complete
d. Documentation | Write "how to" documination on how to confgure NPSP | 1a-c | Dipesh | 2015-02-10 | 2015-02-13 | 3 | Complete
2. Set-up 4 diffferent tiered user accounts
a. SalesForce Master Accunt | Master Account Access | 1b | Dipesh | 2015-02-13 | 2015-02-15 | 2 | Complete
b. Independent Arts and Media | User Account Access: Can only see records that are assicoated with IAM Orginzation | 1b | Dipesh | 2015-02-13 | 2015-02-15 | 2 | Complete
c. Wavelength | User Account Access: Can only see records that are assicoated with Wavelength Orginzation | 1b | Dipesh | 2015-02-13 | 2015-02-15 | 2 | Complete
d. Shapping Shaping San Francisco | User Account Access: Can only see records that are assicoated with Shapping Shaping San Francisco Orginzation | 1b | Dipesh | 2015-02-13 | 2015-02-15 | 2 | Complete
e. Documentation | Write Documentation on how to use and what is expected user access levels for each orginzation. User names and passwords will be profied | 2a-d | Dipesh | 2015-02-15 | 2015-02-18 | 3 | Complete
3. Affilate Projects
3a. Creation of Affilate Projects | Use the Orginzation object to track affilate projects | 1b | Dipesh | 2015-02-18 | 2015-02-25 | 7 | Complete
4. Donartions
4ai. Data Structure | Determine which fields from IAM donor database will be carried over to SalesForce | 1b | Dipesh, Ben, Mathew | 2015-02-25 | 2015-03-01 | 4 | Complete
4aii.Data Stgructure Set Up | Set up the fields in the Donor Object to match the required fileds | 4ai. | Dipesh | 2015-03-01 | 2015-03-05 | 4 | Complete
4bi. Data Onboarding | Export data from IAM and clean the data to match SF requirments | 4aii. | Dipesh | 2015-03-05 | 2015-03-07 | 2 | Complete
4bii. Testing | Validate if the data import | 4bi. | Dipesh, Ben, Mathew | 2015-03-07 | 2015-03-09 | 2 | Complete
4ci. Donor Emails | Write Donor Email Templete for each donor type |  | Lisa, Mathew | 2015-03-09 | 2015-03-12 | 3 | Complete
4cii. Configure Donor Emails | Configure SalesForce to send out automatic donor emails | 4ci. | Dipesh | 2015-03-12 | 2015-03-15 | 3 | Complete
4d. Process to import new Data | Determine what the process of importating new donor data will bef or IAM, Wavelength, and MA | 4bii. | Dipesh | 2015-03-15 | 2015-03-18 | 3 | Complete
4e. Documentation | Write Documenation on how to configure donor data | 4a-d | Dipesh | 2015-03-18 | 2015-03-25 | 7 | Complete
5. Communications
5ai. Mass Email | Determine which mass email solution will be best for the recorded requirements |  | Ben, Dipesh | 2015-03-25 | 2015-03-27 | 2 | Complete
5aii. Mass Email - Set-Up | Set-Up Mail Chimp and link the contacts from SalesForce with Mail Chimp | 5ai. | Dipesh | 2015-03-27 | 2015-04-01 | 5 | Complete
5b. Email Analystics | Set-Up Analystic Reports to track how users interact with each email campaign | 5aii. | Dipesh | 2015-04-01 | 2015-04-03 | 2 | Complete
5c. Petitioning | Set-Up Formual Account to link custom fields into Contacts track Petitions |  | Dipesh | 2015-04-03 | 2015-04-10 | 7 | Complete
5d. Documentation | Write Documenation on how to configure, use and report on each communcation features | 5a-d. | Dipesh | 2015-04-10 | 2015-04-17 | 7 | Complete
Formulas:
Start Date = [Start Date, row above]+[Duration, row above]
Start Date = [Completion Date]-[Duration]